## Sheet1
Name | Duration(weeks) | Predecessors | Resources | Notes
Bear Bank | 49
Planning | 5
Define Processes | 2 |  | Project manager
Set up working environment | 2 |  | Technical Adviser
Build Kanban board | 1 |  | Project manager
Project planning Complete | 0
UI | 8 | 3 |  | Can be done at same time as Database
Homepage | 1 |  | UX Developer
Login | 1 |  | UX Developer
Investment | 1 |  | UX Developer
Account | 1 |  | UX Developer
Cards | 1 |  | UX Developer
Insurance | 1 |  | UX Developer
Tax Service | 1 |  | UX Developer
Verify UI with Owner | 0 |  | Product Owner
Make necessary Changes | 1 |  | UX Developer
UI Complete | 0
Database | 9 | 3 |  | Can be done at same time as UI
Design database | 2 |  | Reporting Developer
Build database | 4 |  | Reporting Developer
Test database | 2 |  | Test Engineer
Correct issues | 1 |  | Reporting Developer
Database Complete | 0
Site Programming | 16 | 3,8,17
Database Calls | 2 |  | Lead Developer
Homepage | 2 |  | Lead Developer
Login | 2 |  | Lead Developer
Investment | 2 |  | Lead Developer
Account | 2 |  | Lead Developer
Cards | 2 |  | Lead Developer
Insurance | 2 |  | Lead Developer
Tax Service | 2 |  | Lead Developer
Site Complete | 0
Security Verification | 6 | 3,8,17,23
Find security issues | 3 |  | Cyber analyst
Fix security issues | 1 |  | Lead Developer
Test security issues | 1 |  | Cyber analyst
Fix Test results | 1 |  | Lead Developer
Obtain HTTPS Cert. | 0 |  | Project manager
Security Complete | 0
Final Testing | 5 | 3,8,17,23,33
Software tests | 1 |  | Test Engineer
Endurance tests | 0 |  | Test Engineer
Speed tests | 0 |  | Test Engineer
Fault tests | 0 |  | Test Engineer
Concurrency Tests | 0 |  | Test Engineer
Fix issues from software tests | 1 |  | Lead Developer
UAT | 2 |  | Test Engineer
Fix issues from UAT | 1 |  | Lead Developer
Testing Complete | 0
Project End | 0 | 40
Obtain Final Sign off | 0 |  | Product Owner
Provide Report out | 0 |  | Project manager